## Top questions
Two Labs Compliance Platform: top questions for a strong solution
Highest value questions for EPG. Assumptions are Hexaware working positions, to be confirmed with EPG. Clarification questions are due Fri Oct 9; data room items are requested for shortlisted vendors.
# | Priority | Area | Question | Why it matters (design decision) | Who to ask | Needed by | Answer / status
1 | High | Commercial | Is a fixed price by phase acceptable, or is another commercial model preferred, and is there a target or ceiling for build cost and annual run cost? | Shapes price structure, risk sharing and the scope shown against optional groups. | EPG procurement | Oct 9 | This is a Hexaware driver . they prefer Outcome based Fixed price model
2 | High | Existing systems | Can vendors access the data room (user guides, technical overviews, anonymised intake data, DPT rule catalogue, report formats) before Oct 19? | Confirms reuse of knowledge and data and the size of migration. | EPG procurement | Oct 9
3 | High | Sequencing | Which module goes live first, and are client features (stage 2) expected with the internal tool or after it? | Sets the order of the 14 month plan and when the client portal is built. | Business sponsor | Oct 9
4 | High | State Licensing | How many distribution models, licence types and document rules sit in the filing plan and document spreadsheets, and how often do they change? | Sizes the determination rule set and the rules owner workload (SL-03). | Two Labs licensing lead | Data room
5 | High | State Licensing | How many state application forms and versions exist, in what formats, and which states require filing through an online portal? | Drives the form template approach, currency checks and the portal adapter roadmap (SL-05, FUT-01). | Two Labs licensing lead | Data room
6 | High | Drug Price Transparency | Can Two Labs share the DPT state rule catalogue, including operators, look-back windows and Medicare Part D thresholds by year? | Defines the rule data model and the regression cases (DPT-02, CLR-01 to 05). | Two Labs DPT lead | Data room
7 | High | Drug Price Transparency | Which state report formats are fixed files, which are web forms and which need manual steps? | Sets the report generator design and effort (DPT-06). | Two Labs DPT lead | Data room
8 | High | Rules governance | Who owns rule definitions and sign off, and how many SME hours a week are available during the build? | Limited SME time is the largest schedule risk. | Two Labs leadership | Oct 9
9 | High | Data | How clean are the existing licence, project, price and document records, and what is the document volume and retention requirement? | Drives migration profiling, load waves and storage design. | Two Labs operations | Data room
10 | High | Security | Which security standards or attestations are expected (for example SOC 2 or ISO 27001), and may EPG audit the vendor? | Defines control mapping, assurance cost and the penetration test scope. | EPG security | Oct 9
11 | High | Security | Which sensitive fields (SSNs, dates of birth, state system credentials) must be stored, and what handling and retention apply? | Sets field level protection and what the platform retains. | EPG privacy | Oct 9
12 | Medium | Identity | Which clients expect single sign on, with which identity providers, and what identity does Two Labs staff use? | Identity design and the scope of OPT-12. | EPG IT | Discovery
13 | Medium | Hosting | Is an EPG owned or Hexaware operated AWS account preferred, and are there EPG cloud standards to follow? | Operating model, access and exit terms. | EPG IT | Oct 9 | Why are we taking this on us ? buuld it on their AWS account
14 | Medium | Content rights | Does EPG hold client facing rights to compendia and legislative tracking data, and who pays the fees? | Gates client features and run cost. | EPG product owner | Oct 9 | EPG has to pay the fees . why ask who pays the fees ? we should confirm that they get this data
15 | Medium | Scale | What client user counts per stage and client organisation growth over five years should the platform be sized for? | Capacity sizing and run cost. | Two Labs leadership | Discovery
16 | Medium | Options | Which of the 18 optional capability groups does Two Labs expect to buy in year one, and is AI assisted work (OPT-07, OPT-16) acceptable? | Which options to design in from day one. | Business sponsor | Oct 9
17 | Medium | Operations | Who operates the platform after handover, with what skills and team size, and what training and support period is expected? | Documentation, hypercare length and run cost. | Two Labs leadership | Discovery | We should have a support plan assuming we continue IT support and also a exit plan in case they want to take over .
18 |  | Business | Confirm the implementation priority and sequencing across State Licensing, DPT, and shared capabilities. Is State Licensing expected to be delivered first? | Phasing, schedule and staffing
19 |  | Business | Must all 211 required requirements be delivered before the first production release, or may vendors propose a phased MVP and subsequent releases? | Release strategy, estimate and timeline
20 |  | Business | What measurable outcomes and baselines should the solution target, such as reduced manual effort, faster processing, on-time submissions, lower cost to serve, and client adoption? | Benefits case and KPI design
21 |  | Business | What proportion of clients is expected to use managed service, hybrid service, and standalone self-service during the evaluation period? | User model, demand and support sizing
22 |  | Business | Confirm the TCO evaluation period and projected growth in clients, users, licences, facilities, projects, NDCs, reports, documents, and transactions. | Sizing, pricing and TCO
23 |  | Functional / Process | Confirm the target operating processes for managed-service, hybrid, and standalone clients, including which activities clients may perform without Two Labs review. | Workflow and control design
24 |  | Functional / Process | Under full self-service, should clients receive the same capabilities as internal users, or a separate client-side function set with different controls? | UX, roles and security
25 |  | Functional / Process | Can standalone DPT outputs be released without Two Labs review? If so, what accuracy evidence, approval record, or disclaimer must accompany them? | Approval workflow and liability
26 |  | Functional / Process | Who will approve State Licensing determination logic, DPT rules, thresholds, state forms, report templates, and regulatory interpretations? | Governance and accountability
27 |  | Technical / Architecture | Provide the technology stack, hosting architecture, source-code status, documentation, interfaces, and support arrangements for both existing applications. | Reuse versus replacement strategy
28 |  | Technical / Architecture | Are vendors expected to reuse, extend, migrate, or replace the existing applications? Are there technical, licensing, ownership, or contractual restrictions on reuse? | Architecture, scope and cost
29 |  | Technical / Architecture | Provide the complete integration inventory, covering connected systems, interface methods, data flows, frequencies, volumes, latency, and ownership. | Integration design and estimate
30 |  | Technical / Architecture | What cloud, identity, SSO, MFA, tenant-isolation, data-residency, availability, RTO, RPO, performance, and concurrent-user requirements should vendors assume? | Platform design and infrastructure sizing
31 |  | Data and Analytics | Provide the complete migration inventory, including sources, formats, record and document volumes, history, data quality, retention requirements, and data owners. | Migration effort and schedule
32 |  | Data and Analytics | Which historical State Licensing data must be migrated from the task-tracking system and document library, and which information may remain available through an archive? | Migration boundary and storage
33 |  | Data and Analytics | What will be the target source of truth for clients, companies, facilities, products, NDCs, licences, rules, reports, subscriptions, and regulatory content? | Data architecture and ownership
34 |  | Operating Model | Confirm the target RACI across Two Labs, EPG, the vendor, and third parties for product ownership, rule maintenance, regulatory content, infrastructure, security, testing, releases, and support. | Operating model and recurring cost
35 |  | Operating Model | What Two Labs and EPG SME capacity should vendors assume for discovery, rule capture, acceptance-criteria definition, regression testing, UAT, and ongoing regulatory updates? | Dependencies, resources and timeline
36 |  | AI and Automation | Which AI capabilities should be included in the base proposal, priced as optional capabilities, or treated only as future considerations? | Scope and commercial classification
37 |  | AI and Automation | For automated document classification, intake review, and checklist placement, what confidence thresholds, human-review controls, exception routes, and acceptance evidence are required? | AI design, testing and controls
38 |  | AI and Automation | May sensitive personal, pricing, trade-secret, and regulatory data be processed by external AI services? What isolation, retention, logging, and model-training restrictions apply? | AI hosting, privacy and security
39 |  | Compliance / Regulatory | Confirm applicable privacy, security, audit, validation, and assurance obligations, including 21 CFR Part 11 or GxP controls, SOC 2, ISO 27001, penetration testing, retention, and audit-trail requirements. | Compliance scope, testing and cost